## Launch Plan
Orée Conseil — Site Launch Plan
oreeconseil.vercel.app becomes the official site at oreeconseil.ca
Prepared for the developer · 10 August 2026
Context: Site B (oree-conseil.ca) was built by Aminata herself, with help from Claude Design, and was given to you as the design/content reference for Site A. Some content was reinterpreted rather than carried over — see the "Content Parity Checklist" sheet for every item that needs to be reviewed before launch.
Priority | Action | Detail | Source | Owner
1 — Critical | Point the domain oreeconseil.ca to Site A | Aminata only — never share the DNS/registrar password. Ask the developer for the DNS values to enter (e.g. the CNAME/A record Vercel provides once the domain is added to the project), then enter them yourself in the registrar's dashboard. Alternative: add the developer as a scoped collaborator on this domain only, if your DNS provider supports it (e.g. Cloudflare). | Two active sites found | Aminata
1 — Critical | Set up 301 redirects from every old URL to its Site A equivalent | index.dc → /, methode.dc → /approach, a-propos.dc → /approach (bio section), pourquoi-oree.dc → / (stats section), offre.dc → /services, contact.dc → /contact. | Preserve existing SEO | Developer
1 — Critical | Set the default language for the Quebec market | Switch the default language to French (or auto-detect by visitor location) instead of English, given the target audience. | Old site displayed FR/EN side by side | Developer
2 — Important | Surface the O·R·É·E mnemonic on the homepage | The 4 method steps (Observer, Relever, Évaluer, Engager) already appear on /approach — bring the same icon treatment onto the homepage for the same immediate impact as the old site. | Present on /approach, not on home | Developer
2 — Important | Expand the FAQ with baseline definitions | Add the questions "What are the ISQ and the CPQ?" and "What is meant by SME?" from the old site — useful for a non-specialist audience. | Old site's FAQ was more complete | Developer
2 — Important | "Formation Orée" / "Law 25 Radar" service gap | Site A does not list a team-training service; should be reintegrated into the official offer. | Offer differs between the two sites | Developer
3 — Nice to have | Standardize the email address everywhere | Make sure no trace of oreeconseil@outlook.com remains (signatures, Google/LinkedIn profiles, etc.) in favor of aminata.diabate@oreeconseil.ca. | Brand consistency | Developer
3 — Nice to have | Update external profiles | Google Business Profile, LinkedIn, email signature: point to oreeconseil.ca, not vercel.app or oree-conseil.ca. | Cross-channel consistency | Developer
3 — Nice to have | Post-migration QA pass | Check all internal links, the contact form, mobile rendering, and the SSL certificate once the domain is repointed. | Final verification | Developer

## Content Parity Checklist
Brand Content to Preserve — Site B → Site A
This is a directive: Site B (oree-conseil.ca) was built by Aminata and carries the elements that distinguish her brand. Every row below is a decision — keep or restore — to apply on Site A before launch.
Source page (Site B) | Content element | Current state on Site A | Decision | Instruction for the developer
Home | Tagline "AI drafts. The human decides." | Present | Keep | Do not remove or reword — this is the brand signature, keep it verbatim.
Home | "Method at a glance" (O·R·É·E icons) | Only on /approach | Restore | Bring the O·R·É·E block (icons + 4 words) back onto the homepage, in the same spot it had on Site B.
Home | "Who it's for" — SMEs, regulated orgs, leadership teams wanting facts, not impressions | Reworded | Restore | Use the exact phrase "facts, not impressions" — it needs to appear as written, not just in substance.
Method | Long-form description of the 4 O·R·É·E steps | Present, reworded | Keep | Meaning is preserved; make sure the 4 verbs (Observe, Uncover, Evaluate, Engage) stay visually prominent as a mnemonic.
About | Full bio text ("Twenty-seven years inside complex organizations...") | Shortened | Restore | Bring back the full-length text, not just the short version — the context for each organization is part of the brand's credibility.
About | Name metaphor: "an orée is the edge of the woods, the place where you stand before stepping in" | Missing | Restore | This line must appear on Site A. It's the explanation of the practice's name — a non-negotiable brand element.
About | Mention of Lean Six Sigma and ADKAR frameworks (CGI engagements) | Missing | Restore | Add this back in full on the About or Approach page — concrete methodological proof, not a vague paraphrase.
About | "Background" list with a sector label per organization (financial institution, telecom, industry, etc.) | Missing (names only, no context) | Restore | Bring back the sector label for each organization, not just an inline list of names.
About | Clarifying line: "Organizations Aminata worked at — not clients" | Missing | Restore — priority 1 | This clarification must be added before launch. Without it, the organization list can be misread as a client list, which is inaccurate and needs correcting without delay.
Why Orée | 4 Quebec statistics (ISQ/CPQ) | Present | Keep | No change needed.
Why Orée | "Cost of inaction" block (widening gap, catching up costs more, ungoverned AI, blind decisions) | Missing | Restore | Bring these 4 statements back as written — they justify the urgency to act and must stay visible on Site A.
Risks | Full page "The cost of inaction" with intro line "The real risk isn't acting on AI too soon — it's acting too late" | Missing | Restore | Recreate this page (or section) on Site A — the intro line must be carried over verbatim.
Risks | Case study: electricity (1879-1920s) | Missing | Restore | Bring back with the same dates and facts.
Risks | Case study: enterprise computing / Solow's paradox (1970-2003) | Missing | Restore | Bring back with the same dates and facts.
Risks | Case study: Nokia / BlackBerry (2007-2016) | Missing | Restore | Bring back with the same dates and facts.
Risks | Case study: Blockbuster vs. Netflix (2000-2010) | Missing | Restore — priority 1 | The most vivid of the four examples. If the developer has to prioritize, restore this one first.
Offering | Orée Diagnostic (3 days) | Present | Keep | No change needed.
Offering | Orée Training (team upskilling) | Missing — replaced by Law 25 Radar | Restore | This service must be reinstated in the official offer, alongside or instead of Law 25 Radar. Confirm with Aminata which one (or both) should appear, but Orée Training should not disappear without an explicit decision.
Offering | Orée Support (monthly follow-up) | Present | Keep | No change needed.
Offering | FAQ: definitions of ISQ, CPQ, SME, "adoption rate" | Missing | Restore | These questions must be added to Site A's FAQ, as written.
Deliverables | Day 1 / Day 2 / Day 3 structure | Present | Keep | No change needed.
Deliverables | Named tool: "Structured interview guide" | Missing | Restore | Name this tool explicitly on Site A, not just describe the process.
Deliverables | Named tool: "The Orée grid" (5 dimensions: cognitive, process, cultural, technical, governance) | Missing | Restore — priority 1 | A core proprietary concept of the Orée method. Must appear under this name, with the 5 dimensions listed.
Deliverables | "Prioritization matrix" (effort / value / risk) | Missing | Restore | Name this tool explicitly, with its 3 criteria (effort, value, risk).
Deliverables | "Debrief report" | Present under a different name (costed action plan) | Keep | Acceptable functional equivalent; confirm the deliverable's actual content matches Site B's description.
Deliverables | "Diagnostic map" (visual organizational summary) | Missing | Restore | Bring back under this name, as an ongoing deliverable beyond the 3 days.
Deliverables | "Progress tracker" (custom indicators) | Missing | Restore | Bring back under this name, as an ongoing deliverable beyond the 3 days.
Deliverables | "Guided implementation" | Present (Orée Support) | Keep | Acceptable functional equivalent.
Contact | Form field: "Organization" | Missing (Name/Email/Phone only) | Restore | Add an Organization field to Site A's form.
Contact | Submission confirmation message | To verify | Restore | Confirm a confirmation message displays after the form is submitted.
Contact | "We reply within one business day" commitment | Present | Keep | No change needed.
General | Email oreeconseil@outlook.com | Replaced by aminata.diabate@oreeconseil.ca | Keep the change | This change is intentional and approved. Every remaining instance of the outlook.com address (site, forms, signatures) must be switched to the oreeconseil.ca domain — do not revert to the old address.
Legend
Keep | Already on Site A — do not alter or lose it during migration
Restore | Missing or weakened on Site A — must be added before launch, not optional